## Slide 1: SWE523 Software Project Management
Failure of Ariane 5 launched on 4th June 1996:
Attempting to fit 64 bits into a 16-bit variable flips the Ariane 5 rocket 90 degrees wrto horizontal bias! What do you think happens!
self destruction mode during the launch, 370 M USD…
https://en.wikipedia.org/wiki/Ariane_5#Notable_launches
A similar failure may cost as high as 5 billion dollars nowadays for the case of 4-5 GEO loaded Ariane 6!

## Slide 2: History's Worst Software Bugs- http://archive.wired.com/software/coolapps/news/2005/11/69355?currentPage=2
1988 -- Buffer overflow in Berkeley Unix finger daemon. The first internet worm (the so-called Morris Worm) infects between 2,000 and 6,000 computers in less than a day by taking advantage of a buffer overflow. The specific code is a function in the standard input/output library routine called gets() designed to get a line of text over the network. Unfortunately, gets() has no provision to limit its input, and an overly large input allows the worm to take over any machine to which it can connect.
Programmers respond by attempting to stamp out the gets() function in working code, but they refuse to remove it from the C programming language's standard input/output library, where it remains to this day.
1988-1996 -- Kerberos Random Number Generator. The authors of the Kerberos security system neglect to properly "seed" the program's random number generator with a truly random seed. As a result, for eight years it is possible to trivially break into any computer that relies on Kerberos for authentication. It is unknown if this bug was ever actually exploited.
January 15, 1990 -- AT&T Network Outage. A bug in a new release of the software that controls AT&T's #4ESS long distance switches causes these mammoth computers to crash when they receive a specific message from one of their neighboring machines -- a message that the neighbors send out when they recover from a crash.
One day a switch in New York crashes and reboots, causing its neighboring switches to crash, then their neighbors' neighbors, and so on. Soon, 114 switches are crashing and rebooting every six seconds, leaving an estimated 60 thousand people without long distance service for nine hours. The fix: engineers load the previous software release.
1993 -- Intel Pentium floating point divide. A silicon error causes Intel's highly promoted Pentium chip to make mistakes when dividing floating-point numbers that occur within a specific range. For example, dividing 4195835.0/3145727.0 yields 1.33374 instead of 1.33382, an error of 0.006 percent. Although the bug affects few users, it becomes a public relations nightmare. With an estimated 3 million to 5 million defective chips in circulation, at first Intel only offers to replace Pentium chips for consumers who can prove that they need high accuracy; eventually the company relents and agrees to replace the chips for anyone who complains. The bug ultimately costs Intel $475 million.
1995/1996 -- The Ping of Death. A lack of sanity checks and error handling in the IP fragmentation reassembly code makes it possible to crash a wide variety of operating systems by sending a malformed "ping" packet from anywhere on the internet. Most obviously affected are computers running Windows, which lock up and display the so-called "blue screen of death" when they receive these packets. But the attack also affects many Macintosh and Unix systems as well.
June 4, 1996 -- Ariane 5 Flight 501. Working code for the Ariane 4 rocket is reused in the Ariane 5, but the Ariane 5's faster engines trigger a bug in an arithmetic routine inside the rocket's flight computer. The error is in the code that converts a 64-bit floating-point number to a 16-bit signed integer. The faster engines cause the 64-bit numbers to be larger in the Ariane 5 than in the Ariane 4, triggering an overflow condition that results in the flight computer crashing.
First Flight 501's backup computer crashes, followed 0.05 seconds later by a crash of the primary computer. As a result of these crashed computers, the rocket's primary processor overpowers the rocket's engines and causes the rocket to disintegrate 40 seconds after launch.
November 2000 -- National Cancer Institute, Panama City. In a series of accidents, therapy planning software created by Multidata Systems International, a U.S. firm, miscalculates the proper dosage of radiation for patients undergoing radiation therapy.
Multidata's software allows a radiation therapist to draw on a computer screen the placement of metal shields called "blocks" designed to protect healthy tissue from the radiation. But the software will only allow technicians to use four shielding blocks, and the Panamanian doctors wish to use five.
The doctors discover that they can trick the software by drawing all five blocks as a single large block with a hole in the middle. What the doctors don't realize is that the Multidata software gives different answers in this configuration depending on how the hole is drawn: draw it in one direction and the correct dose is calculated, draw in another direction and the software recommends twice the necessary exposure.
At least eight patients die, while another 20 receive overdoses likely to cause significant health problems. The physicians, who were legally required to double-check the computer's calculations by hand, are indicted for murder.

## Slide 3: Agenda of this lecture
Content.
Introduction.
  Definitions.
  Discussions.
  Comments.
Part II- R&D Projects

## Slide 4: Contents of this course includes
Software, Project, Management (Defined!).
Overview of project planning.
Software competencies.
Project phases, scheduling.
Planning the work, activities, documents.
Resource management.
Project managers, role, job, processes.
Risk management.
Project Person-month Estimation.

## Slide 5: What Is "Software Project Management"?
Software,
Project, and.
Management

## Slide 6: Software Definition
Software.
  The programs, routines, and symbolic languages that control the functioning of the hardware and direct its operation.

## Slide 7: Project Definition
Project.
  a specific plan or design: SCHEME.
  a planned undertaking: as (a) a definitely formulated piece of research. (b) a large usually government-supported undertaking. (c) a task or problem engaged in usually by a group of students to supplement and apply classroom studies.

## Slide 8: Management Definition.
Management.
  the act or art of managing: the conducting or supervising of something (as a business).
  judicious use of means to accomplish an end.
  the collective body of those who manage or direct an enterprise.

## Slide 9: What Is Software Engineering?
Barry Boehm:
  A practical application of scientific knowledge in the design and construction of computer programs and the associated documentation required to develop, operate, and maintain them.
IEEE:
  a systematic approach to the development, operation, maintenance, and retirement of software.
Stephen Schach:
  discipline whose aim is the production of quality software, software that is delivered on time, within budget, and that satisfies its requirements.

## Slide 10: The Project Management Triangle
Notes: Here, we depict the Project Management Triangle for high quality Projects «most frequenctly» subject to time/schedule, resources/cost and mininum performance requirements.

## Slide 11: Competencies.
Thirty-Four Competencies that Every Software Project Manager Needs to Know

## Slide 12: Product Development Techniques
Assessing processes— Defining criteria for reviews.
Awareness of process standards— Understanding process standards.
Defining the product— Identifying customer environment and product requirements.
Evaluating alternative processes— Evaluating various approaches.
Managing requirements— Monitoring requirements changes.
Managing subcontractors— Planning, managing, and monitoring performance.
Performing the initial assessment— Assessing difficulty, risks, costs, and schedule.
Selecting methods and tools— Defining selection processes.
Tailoring processes— Modifying standard processes to suit a project.
Tracking product quality— Monitoring the quality of an evolving product.
Understanding development activities— Learning the software development cycle.

## Slide 13: Project Management Skills
Building a work breakdown structure— Building a WBS for a project.
Documenting plans— Identifying key components.
Estimating cost— Estimating cost to complete the project.
Estimating effort— Estimating effort required to complete the project.
Managing risks— Identifying and determining the impact and handling of risks.
Monitoring development— Monitoring the production of software.
Scheduling— Creating a schedule and key milestones.
Selecting metrics— Choosing and using appropriate metrics.
Selecting project management tools— Knowing how to select project management tools.
Tracking processes— Monitoring compliance of project team.
Tracking project progress— Monitoring progress using metrics.

## Slide 14: People Management Skills
Appraising performance— Evaluating teams to enhance performance.
Handling intellectual property— Understanding the impact of critical issues.
Holding effective meetings— Planning and running excellent meetings.
Interaction and communication— Dealing with developers, upper management, and other teams.
Leadership— Coaching project teams for optimal results.
Managing change— Being an effective change agent.
Negotiating successfully— Resolving conflicts and negotiating successfully.
Planning careers— Structuring and giving career guidance.
Presenting effectively— Using effective written and oral skills.
Recruiting— Recruiting and interviewing team members successfully.
Selecting a team— Choosing highly competent teams.
Teambuilding— Forming, guiding, and maintaining an effective team.

## Slide 15: What Is a Task? . What Is an Activity?.
Task:
  A generic term for work that is not included in the work breakdown structure, but potentially could be a further decomposition of work by the individuals responsible for that work.
  Also, it is the lowest level of effort on a project.
Activity:
  An element of work performed during the course of a project.
  An activity normally has an expected duration, expected cost, and expected resource requirements.
  Activities can be subdivided into tasks.

## Slide 16: Phase? System?
Phase:
  A collection of related activities or tasks that produce a deliverable or work product.
System:
  An organized group of elements with a boundary defining openness or closeness that acts as a whole toward achieving a common goal.
The IEEE 1074 Software Product Development Life Cycle Model, identifies the referenced phases and lists the software development specific activities for each.

## Slide 17: Iterative Waterfall Software Life Cycle

## Slide 18
Part II- R&D Project,

## Slide 19: Chapter 22 – Project Management
Lecture 2

## Slide 20: Topics covered
Risk management
Managing people
Teamwork

## Slide 21: Software project management
Concerned with activities involved in ensuring that software is delivered on time and on schedule and in accordance with the requirements of the organisations developing and procuring the software.
Project management is needed because software development is always subject to budget and schedule constraints that are set by the organisation developing the software.

## Slide 22: Success criteria
Deliver the software to the customer at the agreed time.
Keep overall costs within budget.
Deliver software that meets the customer’s expectations.
Maintain a happy and well-functioning development team for the next project

## Slide 23: Software management distinctions
The product is intangible.
  Software cannot be seen or touched. Software project managers cannot see progress by simply looking at the artefact that is being constructed.
Many software projects are 'one-off' projects.
  Large software projects are usually different in some ways from previous projects. Even managers who have lots of previous experience may find it difficult to anticipate problems.
Software processes are variable and organization specific.
  We still cannot reliably predict when a particular software process is likely to lead to development problems.

## Slide 24: Management activities
Proposal writing : The first stage in a software project may involve writing a proposal to win a contract to carry out an item of work. The proposal describes the project objectives and how it will be carried out.
Project planning: Project managers are responsible for planning. estimating and scheduling project development and assigning people to tasks.
People management : Project managers have to choose people for their team and establish ways of working that leads to effective team performance
Reporting : Project managers are usually responsible for reporting on the progress of a project to customers and to the managers of the company developing the software.
Risk management: Project managers assess the risks that may affect a project, monitor these risks and take action when problems arise.

## Slide 25: Risk management
A risk is a probability that some adverse circumstance will occur
Risk management is concerned with identifying risks and drawing up plans to minimise their effect on a project.
3 types of risks
  Project risks affect schedule or resources;
  Product risks affect the quality or performance of the software being developed;
  Business risks affect the organisation developing or procuring the software.

## Slide 26: Examples of common project, product, and business risks
Risk | Affects | Description
Staff turnover | Project | Experienced staff will leave the project before it is finished.
Management change | Project | There will be a change of organizational management with different priorities.
Hardware unavailability | Project | Hardware that is essential for the project will not be delivered on schedule.
Requirements change | Project and product | There will be a larger number of changes to the requirements than anticipated.
Specification delays | Project and product | Specifications of essential interfaces are not available on schedule.
Size underestimate | Project and product | The size of the system has been underestimated.
CASE tool underperformance | Product | CASE tools, which support the project, do not perform as anticipated.
Technology change | Business | The underlying technology on which the system is built is superseded by new technology.
Product competition | Business | A competitive product is marketed before the system is completed.

## Slide 27: The risk management process
Risk identification
  Identify project, product and business risks;
Risk analysis
  Assess the likelihood and consequences of these risks;
Risk planning
  Draw up plans to avoid or minimise the effects of the risk;
Risk monitoring
  Monitor the risks throughout the project;

## Slide 28: The risk management process

## Slide 29: Risk identification
May be a team activities or based on the individual project manager’s experience.
A checklist of common risks may be used to identify risks in a project
  Technology risks.
  People risks.
  Organisational risks.
  Requirements risks.
  Estimation risks.

## Slide 30: Examples of different risk types
Risk type | Possible risks
Technology | The database used in the system cannot process as many transactions per second as expected. (1) Reusable software components contain defects that mean they cannot be reused as planned. (2)
People | It is impossible to recruit staff with the skills required. (3) Key staff are ill and unavailable at critical times. (4) Required training for staff is not available. (5)
Organizational | The organization is restructured so that different management are responsible for the project. (6) Organizational financial problems force reductions in the project budget. (7)
Tools | The code generated by software code generation tools is inefficient. (8) Software tools cannot work together in an integrated way. (9)
Requirements | Changes to requirements that require major design rework are proposed. (10) Customers fail to understand the impact of requirements changes. (11)
Estimation | The time required to develop the software is underestimated. (12) The rate of defect repair is underestimated. (13) The size of the software is underestimated. (14)

## Slide 31: Risk analysis
Assess probability and seriousness of each risk.
Probability may be very low, low, moderate, high or very high.
Risk consequences might be catastrophic, serious, tolerable or insignificant.

## Slide 32: Risk types and examples
Risk | Probability | Effects
Organizational financial problems force reductions in the project budget (7). | Low | Catastrophic
It is impossible to recruit staff with the skills required for the project (3). | High | Catastrophic
Key staff are ill at critical times in the project (4). | Moderate | Serious
Faults in reusable software components have to be repaired before these components are reused. (2). | Moderate | Serious
Changes to requirements that require major design rework are proposed (10). | Moderate | Serious
The organization is restructured so that different management are responsible for the project (6). | High | Serious
The database used in the system cannot process as many transactions per second as expected (1). | Moderate | Serious

## Slide 33: Risk types and examples
Risk | Probability | Effects
The time required to develop the software is underestimated (12). | High | Serious
Software tools cannot be integrated (9). | High | Tolerable
Customers fail to understand the impact of requirements changes (11). | Moderate | Tolerable
Required training for staff is not available (5). | Moderate | Tolerable
The rate of defect repair is underestimated (13). | Moderate | Tolerable
The size of the software is underestimated (14). | High | Tolerable
Code generated by code generation tools is inefficient (8). | Moderate | Insignificant

## Slide 34: Risk planning
Consider each risk and develop a strategy to manage that risk.
Avoidance strategies
  The probability that the risk will arise is reduced;
Minimisation strategies
  The impact of the risk on the project or product will be reduced;
Contingency plans
  If the risk arises, contingency plans are plans to deal with that risk;

## Slide 35: Strategies to help manage risk
Risk | Strategy
Organizational financial problems | Prepare a briefing document for senior management showing how the project is making a very important contribution to the goals of the business and presenting reasons why cuts to the project budget would not be cost-effective.
Recruitment problems | Alert customer to potential difficulties and the possibility of delays; investigate buying-in components.
Staff illness | Reorganize team so that there is more overlap of work and people therefore understand each other’s jobs.
Defective components | Replace potentially defective components with bought-in components of known reliability.
Requirements changes | Derive traceability information to assess requirements change impact; maximize information hiding in the design.

## Slide 36: Strategies to help manage risk
Risk | Strategy
Organizational restructuring | Prepare a briefing document for senior management showing how the project is making a very important contribution to the goals of the business.
Database performance | Investigate the possibility of buying a higher-performance database.
Underestimated development time | Investigate buying-in components; investigate use of a program generator.

## Slide 37: Risk monitoring
Assess each identified risks regularly to decide whether or not it is becoming less or more probable.
Also assess whether the effects of the risk have changed.
Each key risk should be discussed at management progress meetings.

## Slide 38: Risk indicators
Risk type | Potential indicators
Technology | Late delivery of hardware or support software; many reported technology problems.
People | Poor staff morale; poor relationships amongst team members; high staff turnover.
Organizational | Organizational gossip; lack of action by senior management.
Tools | Reluctance by team members to use tools; complaints about CASE tools; demands for higher-powered workstations.
Requirements | Many requirements change requests; customer complaints.
Estimation | Failure to meet agreed schedule; failure to clear reported defects.

## Slide 39: Key points
Good project management is essential if software engineering projects are to be developed on schedule and within budget.
Software management is distinct from other engineering management. Software is intangible. Projects may be novel or innovative with no body of experience to guide their management. Software processes are not as mature as traditional engineering processes.
Risk management is now recognized as one of the most important project management tasks.
Risk management involves identifying and assessing project risks to establish the probability that they will occur and the consequences for the project if that risk does arise. You should make plans to avoid, manage or deal with likely risks if or when they arise.

## Slide 40: Chapter 22 – Project Management
Lecture 3

## Slide 41: Managing people
People are an organisation’s most important assets.
The tasks of a manager are essentially people-oriented. Unless there is some understanding of people, management will be unsuccessful.
Poor people management is an important contributor to project failure.

## Slide 42: People management factors
Consistency
  Team members should all be treated in a comparable way without favourites or discrimination.
Respect
  Different team members have different skills and these differences should be respected.
Inclusion
  Involve all team members and make sure that people’s views are considered.
Honesty
  You should always be honest about what is going well and what is going badly in a project.

## Slide 43: Motivating people
An important role of a manager is to motivate the people working on a project.
Motivation means organizing the work and the working environment to encourage people to work effectively.
  If people are not motivated, they will not be interested in the work they are doing. They will work slowly, be more likely to make mistakes and will not contribute to the broader goals of the team or the organization.
Motivation is a complex issue but it appears that there are different types of motivation based on:
  Basic needs (e.g. food, sleep, etc.);
  Personal needs (e.g. respect, self-esteem);
  Social needs (e.g. to be accepted as part of a group).

## Slide 44: Human needs hierarchy (A. Maslow 1943)
Being valued by others, respect, self-esteem, and self-confidence
Ref: Abraham Maslow (1943) “A Theory of Human Motivation.”

## Slide 45: Need satisfaction
In software development groups, basic physiological and safety needs are not an issue.
Social (Love/belonging)
  Provide communal facilities;
  Allow informal communications e.g. via social networking
Esteem
  Recognition of achievements;
  Appropriate rewards.
Self-realization
  Training - people want to learn more;
  Responsibility.

## Slide 46: Individual motivation
Alice is a software project manager working in a company that develops alarm systems. This company wishes to enter the growing market of assistive technology to help elderly and disabled people live independently. Alice has been asked to lead a team of 6 developers than can develop new products based around the company’s alarm technology.
Alice’s assistive technology project starts well. Good working relationships develop within the team and creative new ideas are developed. The team decides to develop a peer-to-peer messaging system using digital televisions linked to the alarm network for communications. However, some months into the project, Alice notices that Dorothy, a hardware design expert, starts coming into work late, the quality of her work deteriorates and, increasingly, that she does not appear to be communicating with other members of the team.
Alice talks about the problem informally with other team members to try to find out if Dorothy’s personal circumstances have changed, and if this might be affecting her work. They don’t know of anything, so Alice decides to talk with Dorothy to try to understand the problem.
Notes: Just let student’s read this. Don’t try to read it out in class. Talk around the issues discussed in the book.

## Slide 47: Individual motivation
After some initial denials that there is a problem, Dorothy admits that she has lost interest in the job. She expected that she would be able to develop and use her hardware interfacing skills. However, because of the product direction that has been chosen, she has little opportunity for this. Basically, she is working as a C programmer with other team members.
Although she admits that the work is challenging, she is concerned that she is not developing her interfacing skills. She is worried that finding a job that involves hardware interfacing will be difficult after this project. Because she does not want to upset the team by revealing that she is thinking about the next project, she has decided that it is best to minimize conversation with them.

## Slide 48: Personality types
The needs hierarchy is almost certainly an over-simplification of motivation in practice.
Motivation should also take into account different personality types:
  Task-oriented;
  Self-oriented;
  Interaction-oriented.

## Slide 49: Personality types
Task-oriented.
  The motivation for doing the work is the work itself;
Self-oriented.
  The work is a means to an end which is the achievement of individual goals - e.g. to get rich, to play tennis, to travel etc.;
Interaction-oriented
  The principal motivation is the presence and actions of co-workers. People go to work because they like to go to work.

## Slide 50: Motivation balance
Individual motivations are made up of elements of each class.
The balance can change depending on personal circumstances and external events.
However, people are not just motivated by personal factors but also by being part of a group and culture.
People go to work because they are motivated by the people that they work with.

## Slide 51: Teamwork
Most software engineering is a group activity
  The development schedule for most non-trivial software projects is such that they cannot be completed by one person working alone.
A good group is cohesive and has a team spirit. The people involved are motivated by the success of the group as well as by their own personal goals.
Group interaction is a key determinant of group performance.
Flexibility in group composition is limited
  Managers must do the best they can with available people.

## Slide 52: Group cohesiveness
In a cohesive group, members consider the group to be more important than any individual in it.
The advantages of a cohesive group are:
  Group quality standards can be developed by the group members.
  Team members learn from each other and get to know each other’s work; Inhibitions caused by ignorance are reduced.
  Knowledge is shared. Continuity can be maintained if a group member leaves.
  Refactoring and continual improvement is encouraged. Group members work collectively to deliver high quality results and fix problems, irrespective of the individuals who originally created the design or program.

## Slide 53: Team spirit
Alice, an experienced project manager, understands the importance of creating a cohesive group. As they are developing a new product, she takes the opportunity of involving all group members in the product specification and design by getting them to discuss possible technology with elderly members of their families. She also encourages them to bring these family members to meet other members of the development group.
Alice also arranges monthly lunches for everyone in the group. These lunches are an opportunity for all team members to meet informally, talk around issues of concern, and get to know each other. At the lunch, Alice tells the group what she knows about organizational news, policies, strategies, and so forth. Each team member then briefly summarizes what they have been doing and the group discusses a general topic, such as new product ideas from elderly relatives.
Every few months, Alice organizes an ‘away day’ for the group where the team spends two days on ‘technology updating’. Each team member prepares an update on a relevant technology and presents it to the group. This is an off-site meeting in a good hotel and plenty of time is scheduled for discussion and social interaction.
Notes: Same as before – best not to read this out. Talk around the issues after students have had 2 minutes to read it.

## Slide 54: The effectiveness of a team
The people in the group
  You need a mix of people in a project group as software development involves diverse activities such as negotiating with clients, programming, testing and documentation.
The group organization
  A group should be organized so that individuals can contribute to the best of their abilities and tasks can be completed as expected.
Technical and managerial communications
  Good communications between group members, and between the software engineering team and other project stakeholders, is essential.

## Slide 55: Selecting group members
A manager or team leader’s job is to create a cohesive group and organize their group so that they can work together effectively.
This involves creating a group with the right balance of technical skills and personalities, and organizing that group so that the members work together effectively.

## Slide 56: Assembling a team
May not be possible to appoint the ideal people to work on a project
  Project budget may not allow for the use of highly-paid staff;
  Staff with the appropriate experience may not be available;
  An organisation may wish to develop employee skills on a software project.
Managers have to work within these constraints especially when there are shortages of trained staff.

## Slide 57: Group composition
Group composed of members who share the same motivation can be problematic
  Task-oriented - everyone wants to do their own thing;
  Self-oriented - everyone wants to be the boss;
  Interaction-oriented - too much chatting, not enough work.
An effective group has a balance of all types.
This can be difficult to achieve software engineers are often task-oriented.
Interaction-oriented people are very important as they can detect and defuse tensions that arise.

## Slide 58: Group composition
In creating a group for assistive technology development, Alice is aware of the importance of selecting members with complementary personalities. When interviewing potential group members, she tried to assess whether they were task-oriented, self-oriented, or interaction-oriented. She felt that she was primarily a self-oriented type because she considered the project to be a way of getting noticed by senior management and possibly promoted. She therefore looked for one or perhaps two interaction-oriented personalities, with task-oriented individuals to complete the team. The final assessment that she arrived at was:
Alice—self-oriented
Brian—task-oriented
Bob—task-oriented
Carol—interaction-oriented
Dorothy—self-oriented
Ed—interaction-oriented
Fred—task-oriented
Notes: Same as before – discuss the issues around this rather than reading it out.

## Slide 59: Group organization
The way that a group is organized affects the decisions that are made by that group, the ways that information is exchanged and the interactions between the development group and external project stakeholders.
  Key questions include:
    Should the project manager be the technical leader of the group?
    Who will be involved in making critical technical decisions, and how will these be made?
    How will interactions with external stakeholders and senior company management be handled?
    How can groups integrate people who are not co-located?
    How can knowledge be shared across the group?

## Slide 60: Group organization
Small software engineering groups are usually organised informally without a rigid structure.
For large projects, there may be a hierarchical structure where different groups are responsible for different sub-projects.
Agile development is always based around an informal group on the principle that formal structure inhibits information exchange

## Slide 61: Informal groups
The group acts as a whole and comes to a consensus on decisions affecting the system.
The group leader serves as the external interface of the group but does not allocate specific work items.
Rather, work is discussed by the group as a whole and tasks are allocated according to ability and experience.
This approach is successful for groups where all members are experienced and competent.

## Slide 62: Group communications
Good communications are essential for effective group working.
Information must be exchanged on the status of work, design decisions and changes to previous decisions.
Good communications also strengthens group cohesion as it promotes understanding.

## Slide 63: Group communications
Group size
  The larger the group, the harder it is for people to communicate with other group members.
Group structure
  Communication is better in informally structured groups than in hierarchically structured groups.
Group composition
  Communication is better when there are different personality types in a group and when groups are mixed rather than single sex.
The physical work environment
  Good workplace organisation can help encourage communications.

## Slide 64: Key points
People are motivated by interaction with other people, the recognition of management and their peers, and by being given opportunities for personal development.
Software development groups should be fairly small and cohesive. The key factors that influence the effectiveness of a group are the people in that group, the way that it is organized and the communication between group members.
Communications within a group are influenced by factors such as the status of group members, the size of the group, the gender composition of the group, personalities and available communication channels.