## Slide 1: Creating the Work Breakdown Structure

## Slide 2: Why?
If you've got a project charter and an excited customer, why go to the trouble to build a work breakdown structure?

## Slide 3: What is WBS?
  “... a hierarchical list of work activities required to complete a project.”
  “... is a description of the work to be performed, broken down into its key components, to the lowest level.”

## Slide 4: Work breakdowns
can be viewed as
  a tree diagram
  indentions

## Slide 5: Tree View

## Slide 6: Indentions

## Slide 7: WBS is organized...
As major work products and deliverables.
Organize WBS:
  around deliverables and
  the actions to produce those deliverables
Avoid unnecessary work from being done on the project.
  Gold Plating?
  Work that does not drive toward a deliverable. (Avoid!)

## Slide 8: WBS can be created...
as top-down
as bottom-up!

## Slide 9: While breaking down
... until when?
  done by “one unit of resource”
  “Do not plan in any more detail than you can manage!”
... if no WBS?
  BIG BANG!

## Slide 10: Strategy
You should stop when you have a sufficient description of the activity!
Use teams as subgroups rather than individuals.
Not deeper than 3 or 4 levels!
Not a large tree!

## Slide 11: What is milestone?
It must have a deliverable!
Not so close... Not so far...
Stated as “something done” or “something completed”

## Slide 12: What is work package?
It is the lowest level...
Contents:
  Description of the work product expected software element to be produced;
  The staffing requirements who or how many people will do this activity;
  Names of responsible individual(s) who is responsible for seeing that it is completed;
  The scheduled start and end dates when the activity is expected to start and to end;
  The budget assigned (dollars, hours, or other unit) the effort estimate for the activity;
  The acceptance criteria for the work defect level or other quality measure.

## Slide 13: Building a WBS for software
Identify the work concerning the software product (separate from hardware and work processes).
Find any higher system WBS (separate the software from other systems and components).
Determine the software WBS architecture (how to organize this software product and project).
Populate the software WBS architecture (identify all the parts and activities to produce them).
Determine cost categories for software (prepare for estimation activities).

## Slide 14: Identify the Work Concerning Software
Go through the available documentation
  SOW (best item to start with)
  Specifications, concept of operation
  Requirements documents of many kinds
  Design documents
  Standards (internal and external)
  Customer conversations
  Test criteria or expectations
List all items that might impact the cost
Include the what and where of each item

## Slide 15: Find Any Higher System WBS
Determine whether there is a WBS for any higher system (higher project or program) and how the software fits in.

## Slide 16: Determine the Software WBS Architecture

## Slide 17: Populate the Software WBS
Cross-Reference Matrix

## Slide 18: Determine Cost Categories for Software
When necessary to track unit-level costs in a WBS
Determines how the cost will be estimated
  Capital equipment: currency,
  Effort: hours, weeks, or months of labor,
  Overhead items: proportional add-on (a percentage).

## Slide 19: Questions?